## Product Backlog
ID | Categories | Detail (Wiki URL) | Priority | Estimated value | Estimate the initial workload | New estimation of remaining work under Sprint … |  |  |  |  | Thực hiện chuẩn | 2500 | 1875 | 1250 | 625 | 0
[6 empty] | S1 | S2 | S3 | S4 | S5 | Thực hiện hiện tại | 2500 | 1375 | 1125 | 375 | 0
1 | As a user I want to register |  | 1 |  | 100 | 55 | 45 | 15 | 5 | 0
2 | As the user I want to log in |  | 1 |  | 100 | 55 | 45 | 15 | 5 | 0
3 | As Buyer I want to see all services |  | 2 |  | 100 | 55 | 45 | 15 | 5 | 0
4 | As Buyer I want to manage settings |  | 3 |  | 100 | 55 | 45 | 15 | 5 | 0
5 | As Buyer I want to find services |  | 2 |  | 100 | 55 | 45 | 15 | 5 | 0
6 | As Buyer I want to order a service |  | 1 |  | 100 | 55 | 45 | 15 | 5 | 0
7 | As Buyer I want to manage requests |  | 1 |  | 100 | 55 | 45 | 15 | 5 | 0
8 | As Buyer I want to report services |  | 3 |  | 100 | 55 | 45 | 15 | 5 | 0
9 | As Buyer I want to manage orders |  | 1 |  | 100 | 55 | 45 | 15 | 5 | 0
10 | As Seller, I want to report the buyer |  | 3 |  | 100 | 55 | 45 | 15 | 5 | 0
11 | Là Seller tôi muốn quản lý các offer |  | 1 |  | 100 | 55 | 45 | 15 | 5 | 0
12 | As a Seller I want to manage my services |  | 1 |  | 100 | 55 | 45 | 15 | 5 | 0
13 | As Seller, I want to manage orders |  | 1 |  | 100 | 55 | 45 | 15 | 5 | 0
14 | As Seller, I want to see statistics |  | 1 |  | 100 | 55 | 45 | 15 | 5 | 0
15 | Là Seller tôi muốn xem các request và offer của tôi. |  | 1 |  | 100 | 55 | 45 | 15 | 5 | 0
16 | As Seller I want to see my services. |  | 1 |  | 100 | 55 | 45 | 15 | 5 | 0
17 | As Seller I want to see my orders. |  | 1 |  | 100 | 55 | 45 | 15 | 5 | 0
18 | As Seller I want to manage bookings |  | 3 |  | 100 | 55 | 45 | 15 | 5 | 0
19 | As Admin, I want to manage users |  | 2 |  | 100 | 55 | 45 | 15 | 5 | 0
20 | As Admin, I want to manage categories |  | 2 |  | 100 | 55 | 45 | 15 | 5 | 0
21 | As Admin, I want to manage the services |  | 2 |  | 100 | 55 | 45 | 15 | 5 | 0
22 | As Admin, I want to manage reports |  | 2 |  | 100 | 55 | 45 | 15 | 5 | 0
23 | As Admin, I want to manage settings |  | 2 |  | 100 | 55 | 45 | 15 | 5 | 0
24 | As a User, I want to inbox |  | 2 |  | 100 | 55 | 45 | 15 | 5 | 0
25 | As a User, I want to see system notifications |  | 2 |  | 100 | 55 | 45 | 15 | 5 | 0
26 | As an Admin, I want to see statistics |  | 2 |  | 100 | 55 | 45 | 15 | 5 | 0
27 | As Admin, I want to manage the entire system |  | 2 |  | 100 | 55 | 45 | 15 | 5 | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
[6 empty] | 0 | 0 | 0 |  | 0
Note on C1: ====== ID#AAAAD77_VTM (2019-11-13 08:53:46) Mô tả chi tiết về luồng thực hiện chức năng --sinhnx Tue Oct 18 2011 18:13:48 GMT+0700 (SE Asia Standard Time)
Note on F1: ====== ID#AAAAD77_VTc (2019-11-13 08:53:46) Chọn một trong 3 giá trị: [Not Started] [In progress] [Complete] --sinhnx Tue Oct 18 2011 18:14:07 GMT+0700 (SE Asia Standard Time)

## Sprint 1
Items in the Project Backlog | Sprint work | Person made | Estimate the initial workload | New estimates of remaining work | [5 empty] | Công việc hiện tại | 508 | 330 | 330 | 144 | 144 | 73 | 0
|  |  |  | T2 | T3 | T4 | T5 | T6 | T7 | Thực hiện chuẩn | 508 | 423.3333 | 338.6667 | 254 | 169.3333 | 84.6667 | 0
As a user I want to register | Use Case | Thach,Cuong | 8 | 4 | 4 | 2 | 2 | 1 | 0
| ERD Diagram | Linh,Dung | 8 | 4 | 4 | 2 | 2 | 1 | 0
| Design Database | Linh,Dung | 8 | 4 | 4 | 2 | 2 | 2 | 0
As the user I want to log in | Use Case | Cuong | 8 | 4 | 4 | 2 | 2 | 1 | 0
| ERD Diagram | Dung | 8 | 4 | 4 | 2 | 2 | 1 | 0
| Design Database | Linh | 8 | 4 | 4 | 2 | 2 | 1 | 0
As Buyer I want to see all services | Use Case | Thach | 8 | 4 | 4 | 2 | 2 | 1 | 0
| ERD Diagram | Dung | 8 | 4 | 4 | 2 | 2 | 1 | 0
| Design Database | Linh | 8 | 6 | 6 | 2 | 2 | 1 | 0
As Buyer I want to manage settings | Use Case | Cuong | 8 | 6 | 6 | 2 | 2 | 1 | 0
| ERD Diagram | Linh | 8 | 6 | 6 | 2 | 2 | 1 | 0
| Design Database | Linh | 8 | 6 | 6 | 2 | 2 | 1 | 0
As Buyer I want to find services | Use Case | Cuong,Thach | 8 | 6 | 6 | 2 | 2 | 1 | 0
| ERD Diagram | Dung | 8 | 6 | 6 | 2 | 2 | 1 | 0
| Design Database | Thach | 8 | 6 | 6 | 2 | 2 | 1 | 0
As Buyer I want to order a service | Use Case | Thach | 8 | 6 | 6 | 2 | 2 | 1 | 0
| ERD Diagram | Linh,Tung | 8 | 6 | 6 | 2 | 2 | 1 | 0
| Design Database | Tung | 8 | 6 | 6 | 2 | 2 | 1 | 0
As Buyer I want to manage requests | Use Case | Tung | 8 | 6 | 6 | 2 | 2 | 1 | 0
| ERD Diagram | Linh,Tung | 8 | 6 | 6 | 2 | 2 | 1 | 0
| Design Database | Tung | 8 | 6 | 6 | 2 | 2 | 1 | 0
As Buyer I want to report services | Use Case | Thach,Cuong | 8 | 6 | 6 | 2 | 2 | 1 | 0
| ERD Diagram | Linh Tung | 8 | 6 | 6 | 2 | 2 | 1 | 0
| Design Database | Thach | 8 | 4 | 4 | 2 | 2 | 1 | 0
As Buyer I want to manage orders | Use Case | Thach | 8 | 4 | 4 | 2 | 2 | 1 | 0
| ERD Diagram | Linh Dung | 8 | 4 | 4 | 2 | 2 | 1 | 0
| Design Database | Linh | 8 | 4 | 4 | 2 | 2 | 1 | 0
As Seller, I want to report the buyer | Use Case | Cuong | 8 | 4 | 4 | 2 | 2 | 1 | 0
| ERD Diagram | Dung | 8 | 4 | 4 | 2 | 2 | 1 | 0
| Design Database | Thach | 8 | 4 | 4 | 2 | 2 | 1 | 0
As Seller, I want to manage offers | Use Case | Tung,Linh | 8 | 4 | 4 | 2 | 2 | 1 | 0
| ERD Diagram | Linh Dung | 8 | 4 | 4 | 2 | 2 | 1 | 0
| Design Database | Cuong | 8 | 4 | 4 | 2 | 2 | 1 | 0
As a Seller I want to manage my services | Use Case | Tung | 8 | 6 | 6 | 2 | 2 | 1 | 0
| ERD Diagram | Thach | 8 | 6 | 6 | 2 | 2 | 1 | 0
| Design Database | Thach | 8 | 6 | 6 | 2 | 2 | 1 | 0
As Seller, I want to manage orders | Use Case | Cuong | 8 | 6 | 6 | 2 | 2 | 1 | 0
| ERD Diagram | Linh | 8 | 6 | 6 | 2 | 2 | 1 | 0
| Design Database | Dung | 8 | 6 | 6 | 2 | 2 | 1 | 0
As Seller, I want to see statistics | Use Case | Tung | 8 | 4 | 4 | 2 | 2 | 1 | 0
| ERD Diagram | Dung | 8 | 4 | 4 | 2 | 2 | 1 | 0
| Design Database | Linh | 8 | 4 | 4 | 2 | 2 | 1 | 0
As Seller I want to see my requests and offers. | Use Case | Cuong | 8 | 4 | 4 | 2 | 2 | 1 | 0
| ERD Diagram | Linh | 8 | 4 | 4 | 2 | 2 | 1 | 0
| Design Database | Thach | 8 | 4 | 4 | 2 | 2 | 1 | 0
As Seller I want to see my services. | Use Case | Dung | 8 | 4 | 4 | 2 | 2 | 1 | 0
| ERD Diagram | Tung | 8 | 4 | 4 | 2 | 2 | 1 | 0
| Design Database | Cuong | 8 | 4 | 4 | 2 | 2 | 1 | 0
As Seller I want to see my orders. | Use Case | Linh | 8 | 4 | 4 | 2 | 2 | 1 | 0
| ERD Diagram | Thach | 8 | 4 | 4 | 2 | 2 | 1 | 0
| Design Database | Dung | 8 | 4 | 4 | 2 | 2 | 1 | 0
As Seller I want to manage bookings | Use Case | Tung | 8 | 4 | 4 | 2 | 2 | 1 | 0
| ERD Diagram | Cuong | 8 | 4 | 4 | 2 | 2 | 1 | 0
| Design Database | Linh | 4 | 4 | 4 | 2 | 2 | 1 | 0
As Admin, I want to manage users | Use Case | Thach | 4 | 4 | 4 | 2 | 2 | 1 | 0
| ERD Diagram | Dung | 4 | 4 | 4 | 2 | 2 | 1 | 0
| Design Database | Tung | 4 | 4 | 4 | 2 | 2 | 1 | 0
As Admin, I want to manage categories | Use Case | Cuong | 8 | 4 | 4 | 2 | 2 | 1 | 0
| ERD Diagram | Linh | 4 | 4 | 4 | 2 | 2 | 1 | 0
| Design Database | Thach | 4 | 4 | 4 | 2 | 2 | 1 | 0
As Admin, I want to manage the services | Use Case | Dung | 4 | 4 | 4 | 2 | 2 | 1 | 0
| ERD Diagram | Tung | 4 | 4 | 4 | 2 | 2 | 1 | 0
| Design Database | Cuong | 4 | 4 | 4 | 2 | 2 | 1 | 0
As Admin, I want to manage reports | Use Case | Linh | 4 | 4 | 4 | 2 | 2 | 1 | 0
| ERD Diagram | Thach | 4 | 4 | 4 | 2 | 2 | 1 | 0
| Design Database | Dung | 4 | 4 | 4 | 2 | 2 | 1 | 0
As Admin, I want to manage settings | Use Case | Tung | 4 | 4 | 4 | 2 | 2 | 1 | 0
| ERD Diagram | Cuong | 4 | 4 | 4 | 2 | 2 | 1 | 0
| Design Database | Linh | 8 | 4 | 4 | 2 | 2 | 1 | 0
As an Admin, I want to see statistics | Use Case | Thach | 4 | 4 | 4 | 2 | 2 | 1 | 0
| ERD Diagram | Dung | 4 | 4 | 4 | 2 | 2 | 1 | 0
| Design Database | Tung | 4 | 4 | 4 | 2 | 2 | 1 | 0
Note on B1: ====== ID#AAAAD77_VSw (2019-11-13 08:53:46) Một chức năng được chia nhỏ ra thành các phần nhỏ hơn gọi là tác vụ. --sinhnx Tue Oct 18 2011 17:33:20 GMT+0700 (SE Asia Standard Time)
Note on C1: ====== ID#AAAAD77_VTI (2019-11-13 08:53:46) Người thực hiện tác vụ này --sinhnx Tue Oct 18 2011 17:33:05 GMT+0700 (SE Asia Standard Time)
Note on D1: ====== ID#AAAAD77_VTQ (2019-11-13 08:53:46) Thời gian dự kiến hoàn thành (tính theo giờ) --sinhnx Tue Oct 18 2011 18:18:20 GMT+0700 (SE Asia Standard Time)

## Sprint 2
Items in the Project Backlog | Sprint work | Person made | Estimate the initial workload | New estimates of remaining work | [5 empty] | Công việc hiện tại | 540 | 414 | 381 | 192 | 190 | 73 | 0
|  |  |  | T2 | T3 | T4 | T5 | T6 | T7 | Thực hiện chuẩn | 540 | 450 | 360 | 270 | 180 | 90 | 0
As a user I want to register | Activity Diagram | Cả nhóm | 8 | 6 | 4 | 2 | 2 | 1 | 0
| Code Database | Dũng,Linh | 8 | 6 | 4 | 2 | 2 | 1 | 0
| GUI | Thạch,Tùng | 8 | 6 | 4 | 2
| Class Diagram | Cường | 8 | 6 | 4 | 2 | 2 | 2 | 0
As the user I want to log in | Activity Diagram | Cả nhóm | 8 | 6 | 4 | 2 | 2 | 1 | 0
| Code Database | Dũng,Linh | 8 | 6 | 4 | 2 | 2 | 1 | 0
| GUI | Thạch,Tùng | 8 | 6 | 4 | 2 | 2
| Class Diagram | Cường | 8 | 6 | 4 | 2 | 2 | 1 | 0
As Buyer I want to see all services | Activity Diagram | Cả nhóm | 8 | 3 | 4 | 2 | 2 | 1 | 0
| Code Database | Dũng,Linh | 8 | 3 | 4 | 2 | 2 | 1 | 0
| GUI | Thạch,Tùng | 8 | 3 | 4 | 2 | 2
| Class Diagram | Cường | 8 | 3 | 4 | 2 | 2 | 1 | 0
As Buyer I want to manage settings | Activity Diagram | Cả nhóm | 4 | 3 | 4 | 2 | 2 | 1 | 0
| Code Database | Dũng,Linh | 4 | 3 | 4 | 2 | 2 | 1 | 0
| GUI | Thạch,Tùng | 4 | 3 | 4 | 2 | 2
| Class Diagram | Cường | 4 | 3 | 4 | 2 | 2 | 1 | 0
As Buyer I want to find services | Activity Diagram | Cả nhóm | 4 | 3 | 4 | 2 | 2 | 1 | 0
| Code Database | Dũng,Linh | 4 | 3 | 4 | 2 | 2 | 1 | 0
| GUI | Thạch,Tùng | 4 | 3 | 4 | 2 | 2
| Class Diagram | Cường | 4 | 6 | 4 | 2 | 2 | 1 | 0
As Buyer I want to order a service | Activity Diagram | Cả nhóm | 3 | 6 | 4 | 2 | 2 | 1 | 0
| Code Database | Dũng,Linh | 3 | 6 | 4 | 2 | 2 | 1 | 0
| GUI | Thạch,Tùng | 3 | 6 | 4 | 2 | 2
| Class Diagram | Cường | 3 | 6 | 4 | 2 | 2 | 1 | 0
As Buyer I want to manage requests | Activity Diagram | Cả nhóm | 8 | 3 | 4 | 2 | 2 | 1 | 0
| Code Database | Dũng,Linh | 8 | 3 | 4 | 2 | 2 | 1 | 0
| GUI | Thạch,Tùng | 8 | 3 | 4 | 2 | 2
| Class Diagram | Cường | 8 | 3 | 4 | 2 | 2 | 1 | 0
As Buyer I want to report services | Activity Diagram | Cả nhóm | 4 | 3 | 4 | 2 | 2 | 1 | 0
| Code Database | Dũng,Linh | 4 | 2 | 4 | 2 | 2 | 1 | 0
| GUI | Thạch,Tùng | 4 | 2 | 4 | 2 | 2
| Class Diagram | Cường | 4 | 2 | 4 | 2 | 2 | 1 | 0
As Buyer I want to manage orders | Activity Diagram | Cả nhóm | 8 | 3 | 4 | 2 | 2 | 1 | 0
| Code Database | Dũng,Linh | 8 | 3 | 4 | 2 | 2 | 1 | 0
| GUI | Thạch,Tùng | 8 | 3 | 4 | 2 | 2
| Class Diagram | Cường | 8 | 3 | 4 | 2 | 2 | 1 | 0
As Seller, I want to report the buyer | Activity Diagram | Cả nhóm | 4 | 3 | 4 | 2 | 2 | 1 | 0
| Code Database | Dũng,Linh | 4 | 3 | 4 | 2 | 2 | 1 | 0
| GUI | Thạch,Tùng | 4 | 3 | 4 | 2 | 2
| Class Diagram | Cường | 4 | 3 | 3 | 2 | 2 | 1 | 0
As Seller, I want to manage offers | Activity Diagram | Cả nhóm | 8 | 6 | 4 | 2 | 2 | 1 | 0
| Code Database | Dũng,Linh | 8 | 6 | 4 | 2 | 2 | 1 | 0
| GUI | Thạch,Tùng | 8 | 6 | 4 | 2 | 2
| Class Diagram | Cường | 8 | 3 | 4 | 2 | 2 | 1 | 0
As a Seller I want to manage my services | Activity Diagram | Cả nhóm | 8 | 3 | 3 | 2 | 2 | 1 | 0
| Code Database | Dũng,Linh | 8 | 3 | 4 | 2 | 2 | 1 | 0
| GUI | Thạch,Tùng | 8 | 3 | 4 | 2 | 2
| Class Diagram | Cường | 8 | 3 | 4 | 2 | 2 | 1 | 0
As Seller, I want to manage orders | Activity Diagram | Cả nhóm | 8 | 6 | 4 | 2 | 2 | 1 | 0
| Code Database | Dũng,Linh | 8 | 6 | 4 | 2 | 2 | 1 | 0
| GUI | Thạch,Tùng | 8 | 6 | 4 | 2 | 2
| Class Diagram | Cường | 8 | 3 | 4 | 2 | 2 | 1 | 0
As Seller, I want to see statistics | Activity Diagram | Cả nhóm | 4 | 3 | 4 | 2 | 2 | 1 | 0
| Code Database | Dũng,Linh | 4 | 3 | 4 | 2 | 2 | 1 | 0
| GUI | Thạch,Tùng | 4 | 3 | 4 | 2 | 2
| Class Diagram | Cường | 4 | 3 | 4 | 2 | 2 | 1 | 0
As Seller I want to see my requests and offers. | Activity Diagram | Cả nhóm | 8 | 6 | 4 | 2 | 2 | 1 | 0
| Code Database | Dũng,Linh | 8 | 6 | 4 | 2 | 2 | 1 | 0
| GUI | Thạch,Tùng | 8 | 6 | 4 | 2 | 2
| Class Diagram | Cường | 8 | 6 | 4 | 2 | 2 | 1 | 0
As Seller I want to see my services. | Activity Diagram | Cả nhóm | 4 | 6 | 4 | 2 | 2 | 1 | 0
| Code Database | Dũng,Linh | 4 | 6 | 4 | 2 | 2 | 1 | 0
| GUI | Thạch,Tùng | 4 | 6 | 4 | 2 | 2
| Class Diagram | Cường | 4 | 6 | 4 | 2 | 2 | 1 | 0
As Seller I want to see my orders. | Activity Diagram | Cả nhóm | 4 | 6 | 4 | 2 | 2 | 1 | 0
| Code Database | Dũng,Linh | 4 | 6 | 4 | 2 | 2 | 1 | 0
| GUI | Thạch,Tùng | 4 | 6 | 4 | 2 | 2
| Class Diagram | Cường | 4 | 6 | 4 | 2 | 2 | 1 | 0
As Seller I want to manage bookings | Activity Diagram | Cả nhóm | 4 | 3 | 4 | 2 | 2 | 1 | 0
| Code Database | Dũng,Linh | 4 | 3 | 4 | 2 | 2 | 1 | 0
| GUI | Thạch,Tùng | 4 | 3 | 4 | 2 | 2
| Class Diagram | Cường | 4 | 3 | 4 | 2 | 2 | 1 | 0
As Admin, I want to manage users | Activity Diagram | Cả nhóm | 4 | 3 | 4 | 2 | 2 | 1 | 0
| Code Database | Dũng,Linh | 4 | 3 | 3 | 2 | 2 | 1 | 0
| GUI | Thạch,Tùng | 4 | 3 | 4 | 2 | 2
| Class Diagram | Cường | 4 | 3 | 4 | 2 | 2 | 1 | 0
As Admin, I want to manage categories | Activity Diagram | Cả nhóm | 8 | 6 | 4 | 2 | 2 | 1 | 0
| Code Database | Dũng,Linh | 8 | 6 | 4 | 2 | 2 | 1 | 0
| GUI | Thạch,Tùng | 8 | 6 | 4 | 2 | 2
| Class Diagram | Cường | 8 | 6 | 4 | 2 | 2 | 1 | 0
As Admin, I want to manage the services | Activity Diagram | Cả nhóm | 4 | 3 | 4 | 2 | 2 | 1 | 0
| Code Database | Dũng,Linh | 4 | 3 | 4 | 2 | 2 | 1 | 0
| GUI | Thạch,Tùng | 4 | 3 | 4 | 2 | 2
| Class Diagram | Cường | 4 | 3 | 4 | 2 | 2 | 1 | 0
As Admin, I want to manage reports | Activity Diagram | Cả nhóm | 4 | 6 | 4 | 2 | 2 | 1 | 0
| Code Database | Dũng,Linh | 4 | 6 | 4 | 2 | 2 | 1 | 0
| GUI | Thạch,Tùng | 4 | 6 | 4 | 2 | 2
| Class Diagram | Cường | 4 | 6 | 4 | 2 | 2 | 1 | 0
As Admin, I want to manage settings | Activity Diagram | Cả nhóm | 4 | 6 | 4 | 2 | 2 | 1 | 0
| Code Database | Dũng,Linh | 4 | 6 | 4 | 2 | 2 | 1 | 0
| GUI | Thạch,Tùng | 4 | 6 | 4 | 2 | 2
| Class Diagram | Cường | 4 | 6 | 4 | 2 | 2 | 1 | 0
As an Admin, I want to see statistics | Activity Diagram | Cả nhóm | 4 | 3 | 4 | 2 | 2 | 1 | 0
| Code Database | Dũng,Linh | 4 | 3 | 4 | 2 | 2 | 1 | 0
| GUI | Thạch,Tùng | 4 | 3 | 4 | 2 | 2
| Class Diagram | Cường | 4 | 3 | 4 | 2 | 2 | 1 | 0
Note on B1: ====== ID#AAAAD77_VSk (2019-11-13 08:53:46) Một chức năng được chia nhỏ ra thành các phần nhỏ hơn gọi là tác vụ. --sinhnx Tue Oct 18 2011 17:33:20 GMT+0700 (SE Asia Standard Time)
Note on C1: ====== ID#AAAAD77_VSs (2019-11-13 08:53:46) Người thực hiện tác vụ này --sinhnx Tue Oct 18 2011 17:33:05 GMT+0700 (SE Asia Standard Time)
Note on D1: ====== ID#AAAAD77_VTE (2019-11-13 08:53:46) Thời gian dự kiến hoàn thành (tính theo giờ) --sinhnx Tue Oct 18 2011 18:18:20 GMT+0700 (SE Asia Standard Time)

## Sprint 3
Items in the Project Backlog | Sprint work | Person made | Estimate the initial workload | New estimates of remaining work | [5 empty] | Công việc hiện tại | 560 | 435 | 401 | 214 | 212 | 96 | 24
|  |  |  | T2 | T3 | T4 | T5 | T6 | T7 | Thực hiện chuẩn | 560 | 466.6667 | 373.3333 | 280 | 186.6667 | 93.3333 | 0
Model | Tạo class model cho project | Linh, Cường | 8 | 8 | 8 | 8 | 8 | 8 | 8
|  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
|  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
As a user I want to register | Controller | Cường,Linh | 8 | 6 | 4 | 2 | 2 | 1 | 0
| Service | Cường,Linh | 8 | 6 | 4 | 2 | 2 | 1 | 0
| View | Cường,Linh | 8 | 6 | 4 | 2
|  |  | 8 | 6 | 4 | 2 | 2 | 2 | 0
As the user I want to log in | Controller | Cường,Linh | 8 | 6 | 4 | 2 | 2 | 1 | 0
| Service | Cường,Linh | 8 | 6 | 4 | 2 | 2 | 1 | 0
| View | Cường,Linh | 8 | 6 | 4 | 2 | 2
|  |  | 8 | 6 | 4 | 2 | 2 | 1 | 0
As Buyer I want to see all services | Controller | Tùng,Thạch | 8 | 3 | 4 | 2 | 2 | 1 | 0
| Service | Tùng,Thạch | 8 | 3 | 4 | 2 | 2 | 1 | 0
| View | Tùng,Thạch | 8 | 3 | 4 | 2 | 2
|  |  | 8 | 3 | 4 | 2 | 2 | 1 | 0
As Buyer I want to manage settings | Controller | Thạch | 4 | 3 | 4 | 2 | 2 | 1 | 0
| Service | Thạch | 4 | 3 | 4 | 2 | 2 | 1 | 0
| View | Thạch | 4 | 3 | 4 | 2 | 2
|  |  | 4 | 3 | 4 | 2 | 2 | 1 | 0
As Buyer I want to find services | Controller | Linh | 4 | 3 | 4 | 2 | 2 | 1 | 0
| Service | Linh | 4 | 3 | 4 | 2 | 2 | 1 | 0
| View | Linh | 4 | 3 | 4 | 2 | 2
|  |  | 4 | 6 | 4 | 2 | 2 | 1 | 0
As Buyer I want to order a service | Controller | Dũng,Linh | 3 | 6 | 4 | 2 | 2 | 1 | 0
| Service | Dũng,Linh | 3 | 6 | 4 | 2 | 2 | 1 | 0
| View | Dũng,Linh | 3 | 6 | 4 | 2 | 2
|  |  | 3 | 6 | 4 | 2 | 2 | 1 | 0
As Buyer I want to manage requests | Controller | Linh | 8 | 3 | 4 | 2 | 2 | 1 | 0
| Service | Linh | 8 | 3 | 4 | 2 | 2 | 1 | 0
| View | Linh | 8 | 3 | 4 | 2 | 2
|  |  | 8 | 3 | 4 | 2 | 2 | 1 | 0
As Buyer I want to report services | Controller | Linh | 4 | 3 | 4 | 2 | 2 | 1 | 0
| Service | Linh | 4 | 2 | 4 | 2 | 2 | 1 | 0
| View | Linh | 4 | 2 | 4 | 2 | 2
|  |  | 4 | 2 | 4 | 2 | 2 | 1 | 0
As Buyer I want to manage orders | Controller | Linh | 8 | 3 | 4 | 2 | 2 | 1 | 0
| Service | Linh | 8 | 3 | 4 | 2 | 2 | 1 | 0
| View | Linh | 8 | 3 | 4 | 2 | 2
|  |  | 8 | 3 | 4 | 2 | 2 | 1 | 0
As Seller, I want to report the buyer | Controller | Linh | 4 | 3 | 4 | 2 | 2 | 1 | 0
| Service | Linh | 4 | 3 | 4 | 2 | 2 | 1 | 0
| View | Linh | 4 | 3 | 4 | 2 | 2
|  |  | 4 | 3 | 3 | 2 | 2 | 1 | 0
As Seller, I want to manage offers | Controller | Linh | 8 | 6 | 4 | 2 | 2 | 1 | 0
| Service | Linh | 8 | 6 | 4 | 2 | 2 | 1 | 0
| View | Linh | 8 | 6 | 4 | 2 | 2
|  |  | 8 | 3 | 4 | 2 | 2 | 1 | 0
As a Seller I want to manage my services | Controller | Dũng,Thạch | 8 | 3 | 3 | 2 | 2 | 1 | 0
| Service | Dũng,Thạch | 8 | 3 | 4 | 2 | 2 | 1 | 0
| View | Dũng,Thạch | 8 | 3 | 4 | 2 | 2
|  |  | 8 | 3 | 4 | 2 | 2 | 1 | 0
As Seller, I want to manage orders | Controller | Dũng,Linh | 8 | 6 | 4 | 2 | 2 | 1 | 0
| Service | Dũng,Linh | 8 | 6 | 4 | 2 | 2 | 1 | 0
| View | Dũng,Linh | 8 | 6 | 4 | 2 | 2
|  |  | 8 | 3 | 4 | 2 | 2 | 1 | 0
As Seller, I want to see statistics | Controller | Dũng,Thạch | 4 | 3 | 4 | 2 | 2 | 1 | 0
| Service | Dũng,Thạch | 4 | 3 | 4 | 2 | 2 | 1 | 0
| View | Dũng,Thạch | 4 | 3 | 4 | 2 | 2
|  |  | 4 | 3 | 4 | 2 | 2 | 1 | 0
As Seller I want to see my requests and offers. | Controller | Tùng,Thạch | 8 | 6 | 4 | 2 | 2 | 1 | 0
| Service | Tùng,Thạch | 8 | 6 | 4 | 2 | 2 | 1 | 0
| View | Tùng,Thạch | 8 | 6 | 4 | 2 | 2
|  | Tùng,Thạch | 8 | 6 | 4 | 2 | 2 | 1 | 0
As Seller I want to see my services. | Controller | Tùng,Thạch | 4 | 6 | 4 | 2 | 2 | 1 | 0
| Service | Tùng,Thạch | 4 | 6 | 4 | 2 | 2 | 1 | 0
| View | Tùng,Thạch | 4 | 6 | 4 | 2 | 2
|  |  | 4 | 6 | 4 | 2 | 2 | 1 | 0
As Seller I want to see my orders. | Controller | Linh,Dũng | 4 | 6 | 4 | 2 | 2 | 1 | 0
| Service | Linh,Dũng | 4 | 6 | 4 | 2 | 2 | 1 | 0
| View | Linh,Dũng | 4 | 6 | 4 | 2 | 2
|  |  | 4 | 6 | 4 | 2 | 2 | 1 | 0
As Seller I want to manage bookings | Controller | Cường | 4 | 3 | 4 | 2 | 2 | 1 | 0
| Service | Cường | 4 | 3 | 4 | 2 | 2 | 1 | 0
| View | Cường | 4 | 3 | 4 | 2 | 2
|  |  | 4 | 3 | 4 | 2 | 2 | 1 | 0
As Admin, I want to manage users | Controller | Linh,Cường | 4 | 3 | 4 | 2 | 2 | 1 | 0
| Service | Linh,Cường | 4 | 3 | 3 | 2 | 2 | 1 | 0
| View | Linh,Cường | 4 | 3 | 4 | 2 | 2
|  |  | 4 | 3 | 4 | 2 | 2 | 1 | 0
As Admin, I want to manage categories | Controller | Cường | 8 | 6 | 4 | 2 | 2 | 1 | 0
| Service | Cường | 8 | 6 | 4 | 2 | 2 | 1 | 0
| View | Cường | 8 | 6 | 4 | 2 | 2
|  |  | 8 | 6 | 4 | 2 | 2 | 1 | 0
As Admin, I want to manage the services | Controller | Dũng,Linh | 4 | 3 | 4 | 2 | 2 | 1 | 0
| Service | Dũng,Linh | 4 | 3 | 4 | 2 | 2 | 1 | 0
| View | Dũng,Linh | 4 | 3 | 4 | 2 | 2
|  | Dũng,Linh | 4 | 3 | 4 | 2 | 2 | 1 | 0
As Admin, I want to manage reports | Controller | Dũng,Linh | 4 | 6 | 4 | 2 | 2 | 1 | 0
| Service | Dũng,Linh | 4 | 6 | 4 | 2 | 2 | 1 | 0
| View | Dũng,Linh | 4 | 6 | 4 | 2 | 2
|  | Dũng,Linh | 4 | 6 | 4 | 2 | 2 | 1 | 0
As Admin, I want to manage settings | Controller | Tùng | 4 | 6 | 4 | 2 | 2 | 1 | 0
| Service | Tùng | 4 | 6 | 4 | 2 | 2 | 1 | 0
| View | Tùng | 4 | 6 | 4 | 2 | 2
|  |  | 4 | 6 | 4 | 2 | 2 | 1 | 0
As an Admin, I want to see statistics | Controller | Tùng | 4 | 3 | 4 | 2 | 2 | 1 | 0
| Service | Tùng | 4 | 3 | 4 | 2 | 2 | 1 | 0
| View | Tùng | 4 | 3 | 4 | 2 | 2
|  |  | 4 | 3 | 4 | 2 | 2 | 1 | 0
Note on B1: ====== ID#AAAAD77_VTg (2019-11-13 08:53:46) Một chức năng được chia nhỏ ra thành các phần nhỏ hơn gọi là tác vụ. --sinhnx Tue Oct 18 2011 17:33:20 GMT+0700 (SE Asia Standard Time)
Note on C1: ====== ID#AAAAD77_VS0 (2019-11-13 08:53:46) Người thực hiện tác vụ này --sinhnx Tue Oct 18 2011 17:33:05 GMT+0700 (SE Asia Standard Time)
Note on D1: ====== ID#AAAAD77_VTU (2019-11-13 08:53:46) Thời gian dự kiến hoàn thành (tính theo giờ) --sinhnx Tue Oct 18 2011 18:18:20 GMT+0700 (SE Asia Standard Time)

## Sprint 4
Items in the Project Backlog | Sprint work | Person made | Estimate the initial workload | New estimates of remaining work | [5 empty] | Công việc hiện tại | 716 | 559 | 278 | 140 | 140 | 47 | 0
|  |  |  | T2 | T3 | T4 | T5 | T6 | T7 | Thực hiện chuẩn | 716 | 596.6667 | 477.3333 | 358 | 238.6667 | 119.3333 | 0
As the user I want to log in | Controller | Cường,Linh | 12 | 12 | 4 | 2 | 2 | 1 | 0
| Service | Cường,Linh | 12 | 8 | 4 | 2 | 2 | 1 | 0
| View | Cường,Linh | 12 | 12 | 4 | 2 | 2 | 0 | 0
As Buyer I want to see all services | Controller | Tùng,Thạch | 12 | 12 | 4 | 2 | 2 | 1 | 0
| Service | Tùng,Thạch | 12 | 8 | 4 | 2 | 2 | 1 | 0
| View | Tùng,Thạch | 12 | 8 | 4 | 2 | 2 | 0 | 0
As Buyer I want to manage settings | Controller | Thạch | 12 | 8 | 4 | 2 | 2 | 1 | 0
| Service | Thạch | 12 | 8 | 4 | 2 | 2 | 1 | 0
| View | Thạch | 12 | 8 | 4 | 2 | 2 | 0 | 0
As Buyer I want to find services | Controller | Linh | 12 | 12 | 4 | 2 | 2 | 1 | 0
| Service | Linh | 12 | 12 | 4 | 2 | 2 | 1 | 0
| View | Linh | 12 | 12 | 4 | 2 | 2 | 0 | 0
As Buyer I want to order a service | Controller | Dũng,Linh | 12 | 12 | 4 | 2 | 2 | 1 | 0
| Service | Dũng,Linh | 12 | 12 | 4 | 2 | 2 | 1 | 0
| View | Dũng,Linh | 12 | 12 | 4 | 2 | 2 | 0 | 0
As Buyer I want to manage requests | Controller | Linh | 12 | 12 | 4 | 2 | 2 | 1 | 0
| Service | Linh | 12 | 12 | 4 | 2 | 2 | 1 | 0
| View | Linh | 12 | 12 | 4 | 2 | 2 | 0 | 0
As Buyer I want to report services | Controller | Linh | 8 | 8 | 4 | 2 | 2 | 1 | 0
| Service | Linh | 8 | 8 | 4 | 2 | 2 | 1 | 0
| View | Linh | 8 | 8 | 4 | 2 | 2 | 0 | 0
As Buyer I want to manage orders | Controller | Linh | 12 | 12 | 4 | 2 | 2 | 1 | 0
| Service | Linh | 12 | 12 | 4 | 2 | 2 | 1 | 0
| View | Linh | 12 | 12 | 4 | 2 | 2
As Seller, I want to report the buyer | Controller | Linh | 8 | 8 | 4 | 2 | 2 | 1 | 0
| Service | Linh | 8 | 8 | 4 | 2 | 2 | 1 | 0
| View | Linh | 8 | 8 | 4 | 2 | 2 | 0 | 0
As Seller, I want to manage offers | Controller | Linh | 12 | 8 | 4 | 2 | 2 | 1 | 0
| Service | Linh | 12 | 8 | 4 | 2 | 2 | 1 | 0
| View | Linh | 12 | 12 | 4 | 2 | 2 | 0 | 0
As a Seller I want to manage my services | Controller | Dũng,Thạch | 12 | 8 | 3 | 2 | 2 | 1 | 0
| Service | Dũng,Thạch | 12 | 12 | 4 | 2 | 2 | 1 | 0
| View | Dũng,Thạch | 12 | 12 | 4 | 2 | 2 | 0 | 0
As Seller, I want to manage orders | Controller | Dũng,Linh | 12 | 8 | 4 | 2 | 2 | 1 | 0
| Service | Dũng,Linh | 12 | 8 | 4 | 2 | 2 | 1 | 0
| View | Dũng,Linh | 12 | 8 | 4 | 2 | 2 | 0
0
As Seller, I want to see statistics | Controller | Dũng,Thạch | 12 | 8 | 4 | 2 | 2 | 1 | 0
| Service | Dũng,Thạch | 12 | 8 | 4 | 2 | 2 | 1 | 0
| View | Dũng,Thạch | 12 | 8 | 4 | 2 | 2
As Seller I want to see my requests and offers. | Controller | Tùng,Thạch | 12 | 8 | 4 | 2 | 2 | 1 | 0
| Service | Tùng,Thạch | 12 | 8 | 4 | 2 | 2 | 1 | 0
| View | Tùng,Thạch | 12 | 12 | 4 | 2 | 2 | 0 | 0
8
As Seller I want to see my services. | Controller | Tùng,Thạch | 8 | 6 | 4 | 2 | 2 | 1 | 0
| Service | Tùng,Thạch | 8 | 6 | 4 | 2 | 2 | 1 | 0
| View | Tùng,Thạch | 8 | 6 | 4 | 2 | 2 | 0 | 0
As Seller I want to see my orders. | Controller | Linh,Dũng | 8 | 6 | 4 | 2 | 2 | 1 | 0
| Service | Linh,Dũng | 8 | 6 | 4 | 2 | 2 | 1 | 0
| View | Linh,Dũng | 8 | 6 | 4 | 2 | 2 | 0 | 0
As Seller I want to manage settings | Controller | Cường | 8 | 4 | 4 | 2 | 2 | 1 | 0
| Service | Cường | 8 | 4 | 4 | 2 | 2 | 1 | 0
| View | Cường | 8 | 8 | 4 | 2 | 2 | 0
0
As Admin, I want to manage users | Controller | Linh,Cường | 8 | 4 | 4 | 2 | 2 | 1 | 0
| Service | Linh,Cường | 8 | 4 | 3 | 2 | 2 | 1 | 0
| View | Linh,Cường | 8 | 4 | 4 | 2 | 2 | 0 | 0
As Admin, I want to manage categories | Controller | Cường | 12 | 6 | 4 | 2 | 2 | 1 | 0
| Service | Cường | 12 | 6 | 4 | 2 | 2 | 1 | 0
| View | Cường | 12 | 6 | 4 | 2 | 2 | 0 | 0
As Admin, I want to manage the services | Controller | Dũng,Linh | 8 | 3 | 4 | 2 | 2 | 1 | 0
| Service | Dũng,Linh | 8 | 3 | 4 | 2 | 2 | 1 | 0
| View | Dũng,Linh | 8 | 3 | 4 | 2 | 2 | 0 | 0
|  | Dũng,Linh | 8 | 3 | 4 | 2 | 2 | 1 | 0
As Admin, I want to manage reports | Controller | Dũng,Linh | 8 | 6 | 4 | 2 | 2 | 1 | 0
| Service | Dũng,Linh | 8 | 6 | 4 | 2 | 2 | 1 | 0
| View | Dũng,Linh | 8 | 6 | 4 | 2 | 2 | 0 | 0
As Admin, I want to manage settings | Controller | Tùng | 8 | 6 | 4 | 2 | 2 | 1 | 0
| Service | Tùng | 8 | 6 | 4 | 2 | 2 | 1 | 0
| View | Tùng | 8 | 6 | 4 | 2 | 2
As an Admin, I want to see statistics | Controller | Tùng | 8 | 3 | 4 | 2 | 2 | 1 | 0
| Service | Tùng | 8 | 3 | 4 | 2 | 2 | 1 | 0
| View | Tùng | 8 | 3 | 4 | 2 | 2 | 0 | 0
Note on B1: ====== ID#AAAAD77_VTA (2019-11-13 08:53:46) Một chức năng được chia nhỏ ra thành các phần nhỏ hơn gọi là tác vụ. --sinhnx Tue Oct 18 2011 17:33:20 GMT+0700 (SE Asia Standard Time)
Note on C1: ====== ID#AAAAD77_VTk (2019-11-13 08:53:46) Người thực hiện tác vụ này --sinhnx Tue Oct 18 2011 17:33:05 GMT+0700 (SE Asia Standard Time)
Note on D1: ====== ID#AAAAD77_VSo (2019-11-13 08:53:46) Thời gian dự kiến hoàn thành (tính theo giờ) --sinhnx Tue Oct 18 2011 18:18:20 GMT+0700 (SE Asia Standard Time)

## Sprint 5
Items in the Project Backlog | Sprint work | Person made | Estimate the initial workload | New estimates of remaining work | [5 empty] | Công việc hiện tại | 552 | 408 | 184 | 92 | 92 | 46 | 0
|  |  |  | T2 | T3 | T4 | T5 | T6 | T7 | Thực hiện chuẩn | 552 | 460 | 368 | 276 | 184 | 92 | 0
As the user I want to log in | Sequence Diagram | Cả nhóm | 12 | 8 | 4 | 2 | 2 | 1 | 0
| Testing | Dũng | 12 | 8 | 4 | 2 | 2 | 1 | 0
As Buyer I want to see all services | Sequence Diagram | Cả nhóm | 12 | 8 | 4 | 2 | 2 | 1 | 0
| Testing | Dũng | 12 | 8 | 4 | 2 | 2 | 1 | 0
As Buyer I want to manage settings | Sequence Diagram | Cả nhóm | 12 | 8 | 4 | 2 | 2 | 1 | 0
| Testing | Dũng | 12 | 8 | 4 | 2 | 2 | 1 | 0
As Buyer I want to find services | Sequence Diagram | Cả nhóm | 12 | 8 | 4 | 2 | 2 | 1 | 0
| Testing | Dũng | 12 | 8 | 4 | 2 | 2 | 1 | 0
As Buyer I want to order a service | Sequence Diagram | Cả nhóm | 12 | 8 | 4 | 2 | 2 | 1 | 0
| Testing | Dũng | 12 | 8 | 4 | 2 | 2 | 1 | 0
As Buyer I want to manage requests | Sequence Diagram | Cả nhóm | 12 | 8 | 4 | 2 | 2 | 1 | 0
| Testing | Dũng | 12 | 8 | 4 | 2 | 2 | 1 | 0
As Buyer I want to report services | Sequence Diagram | Cả nhóm | 12 | 8 | 4 | 2 | 2 | 1 | 0
| Testing | Dũng | 12 | 8 | 4 | 2 | 2 | 1 | 0
As Buyer I want to manage orders | Sequence Diagram | Cả nhóm | 12 | 8 | 4 | 2 | 2 | 1 | 0
| Testing | Dũng | 12 | 8 | 4 | 2 | 2 | 1 | 0
As Seller, I want to report the buyer | Sequence Diagram | Cả nhóm | 12 | 8 | 4 | 2 | 2 | 1 | 0
| Testing | Dũng | 12 | 8 | 4 | 2 | 2 | 1 | 0
As Seller, I want to manage offers | Sequence Diagram | Cả nhóm | 12 | 8 | 4 | 2 | 2 | 1 | 0
| Testing | Dũng | 12 | 8 | 4 | 2 | 2 | 1 | 0
As a Seller I want to manage my services | Sequence Diagram | Cả nhóm | 12 | 8 | 4 | 2 | 2 | 1 | 0
| Testing | Dũng | 12 | 8 | 4 | 2 | 2 | 1 | 0
As Seller, I want to manage orders | Sequence Diagram | Cả nhóm | 12 | 8 | 4 | 2 | 2 | 1 | 0
| Testing | Dũng | 12 | 8 | 4 | 2 | 2 | 1 | 0
As Seller, I want to see statistics | Sequence Diagram | Cả nhóm | 12 | 8 | 4 | 2 | 2 | 1 | 0
| Testing | Dũng | 12 | 8 | 4 | 2 | 2 | 1 | 0
As Seller I want to see my requests and offers. | Sequence Diagram | Cả nhóm | 12 | 12 | 4 | 2 | 2 | 1 | 0
| Testing | Dũng | 12 | 8 | 4 | 2 | 2 | 1 | 0
As Seller I want to see my services. | Sequence Diagram | Cả nhóm | 12 | 12 | 4 | 2 | 2 | 1 | 0
| Testing | Dũng | 12 | 8 | 4 | 2 | 2 | 1 | 0
As Seller I want to see my orders. | Sequence Diagram | Cả nhóm | 12 | 12 | 4 | 2 | 2 | 1 | 0
| Testing | Dũng | 12 | 8 | 4 | 2 | 2 | 1 | 0
As Seller I want to see my orders. | Sequence Diagram | Cả nhóm | 12 | 12 | 4 | 2 | 2 | 1 | 0
| Testing | Dũng | 12 | 8 | 4 | 2 | 2 | 1 | 0
As Admin, I want to manage users | Sequence Diagram | Cả nhóm | 12 | 12 | 4 | 2 | 2 | 1 | 0
| Testing | Dũng | 12 | 8 | 4 | 2 | 2 | 1 | 0
As Admin, I want to manage categories | Sequence Diagram | Cả nhóm | 12 | 12 | 4 | 2 | 2 | 1 | 0
| Testing | Dũng | 12 | 8 | 4 | 2 | 2 | 1 | 0
As Admin, I want to manage the services | Sequence Diagram | Cả nhóm | 12 | 12 | 4 | 2 | 2 | 1 | 0
| Testing | Dũng | 12 | 8 | 4 | 2 | 2 | 1 | 0
As Admin, I want to manage reports | Sequence Diagram | Cả nhóm | 12 | 12 | 4 | 2 | 2 | 1 | 0
| Testing | Dũng | 12 | 8 | 4 | 2 | 2 | 1 | 0
As Admin, I want to manage settings | Sequence Diagram | Cả nhóm | 12 | 12 | 4 | 2 | 2 | 1 | 0
| Testing | Dũng | 12 | 8 | 4 | 2 | 2 | 1 | 0
As an Admin, I want to see statistics | Sequence Diagram | Cả nhóm | 12 | 12 | 4 | 2 | 2 | 1 | 0
| Testing | Dũng | 12 | 8 | 4 | 2 | 2 | 1 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Note on B1: ====== ID#AAAAD77_VTY (2019-11-13 08:53:46) Một chức năng được chia nhỏ ra thành các phần nhỏ hơn gọi là tác vụ. --sinhnx Tue Oct 18 2011 17:33:20 GMT+0700 (SE Asia Standard Time)
Note on C1: ====== ID#AAAAD77_VS4 (2019-11-13 08:53:46) Người thực hiện tác vụ này --sinhnx Tue Oct 18 2011 17:33:05 GMT+0700 (SE Asia Standard Time)
Note on D1: ====== ID#AAAAD77_VS8 (2019-11-13 08:53:46) Thời gian dự kiến hoàn thành (tính theo giờ) --sinhnx Tue Oct 18 2011 18:18:20 GMT+0700 (SE Asia Standard Time)

## logs
Date | Developer | Đã làm gì? | Sẽ làm gì? | Gặp khó khăn gì không?
SPRINT 1
18/10/2019- 21/10/2019 | Cả nhóm | Xác định đề tài
| Cả nhóm | Use Case | Tập Hợp các use case mô tả use case | Khó khăn trong việc xác định use case hệ thông
21/20/2019-25/10/2019 | Cả nhóm | Vẽ use case | Tập Hợp các use case mô tả use case | Khó khăn trong việc xác định use case hệ thông
| Cả nhóm | Entity Relationship Diagram | Vẽ Entity relationship diagram
| Cả nhóm | ERD | Mô tả tri tiết từng thục thể. | Xác định thực thể
SPRINT 2
28/10/2019-30/10/2019 | Cả nhóm | Vẽ use case diagram | Vẽ các use case chi tiết hơn
| Cả nhóm | Vẽ Activiti diagram | Mô tả hoạt đọng từng use case
01/11/2019 -06/11/2019 | Cả nhóm | Database diagram | Thiết kế cơ sở dự liệu
| Dũng, Linh | Code database
| Cường | Class diagram | Thiết kế class
01/11/2019- 06/11/2019 | Tùng | Mô hình code | Thiết kế mô hình hệ thống freelancer
SPRINT 3
11/11/2019-15/11/2019 | Dũng, Thach | Controller, Service,View | Code phần tạo dich vụ cho seller
| Cường | Controller, Service,View | Code phần Login, Register
| Tùng,Linh | Controller, Service,View | Code UI hệ thống
11/11/2019-15/11/2019 | Dũng, Thach | Controller, Service,View | Code phần tạo dich vụ cho seller
| Cường | Controller, Service,View | Code phần add category
| Tùng,Linh | Controller, Service,View | Code UI hệ thống
11/11/2019-15/11/2019 | Dũng, Thach | Controller, Service,View | Code phần order cho buyer
| Cường | Controller, Service,View | Code phần Login, Register
| Tùng,Linh | Controller, Service,View | Code UI hệ thống
11/11/2019-15/11/2019 | Linh,Cường | Controller, Service,View | Code phần Quản lý User
| Cường | Controller, Service,View | Code phần Đăng kí làm seller
| Tùng,Linh | Controller, Service,View | Hiển thị serivice
SPRINT 4
18/11/2019-22/11/2019 | Dũng, Thach | Controller, Service,View | Xem chi tiết dịch vụ
| Cường | Controller, Service,View | Code phần Login, Register
| Tùng,Linh | Controller, Service,View | Code UI hệ thống
18/11/2019-22/11/2019 | Dũng, Thach | Controller, Service,View | Code phần tạo dich vụ cho seller
| Cường | Controller, Service,View | Code phần add category
| Tùng,Linh | Controller, Service,View | Code UI hệ thống
18/11/2019-22/11/2019 | Dũng, Thach | Controller, Service,View | Code phần order cho buyer
| Cường | Controller, Service,View | Code phần Login, Register
| Tùng,Linh | Controller, Service,View | Code UI hệ thống
18/11/2019-22/11/2019 | Linh,Cường | Controller, Service,View | Code phần Quản lý User
| Cường | Controller, Service,View | Code phần Đăng kí làm seller
| Tùng,Linh | Controller, Service,View | Hiển thị serivice
SPRINT 5
25/11/2019- 12/172019 | Dũng,Thạch,Cường | Squence diagram | Vẽ sequence
| Dũng | Document | hoàn thành document và làm bào cáo

## Project-info
Topic: | VTC-Freelancer
Sprint length: | 1 tuần
Number of working days: | 7 ngày
Member
ID Student | Full Name | Title | Number of days in Sprint | Number of hours present during the day | Total hours present
NDE18055 | LÊ CHÍ DŨNG | Developer | 40 | 8 | 320
NDE18048 | ĐOÀN NGỌC THẠCH | Developer | 40 | 8 | 320
NDE18030 | NGUYỄN THANH TÙNG | Developer | 40 | 8 | 320
NDE18090 | NGUYỄN ANH LINH | Developer | 40 | 8 | 320
NDE18020 | ĐẶNG VĂN CƯỜNG | Developer | 40 | 8 | 320